## Sheet1
3 BITI S1G2 GROUP MEMBER: 1. ANG WEI KANG – B032110301 2. LUM FU YUAN – B032110251 3. SIM WENG JIN – B032110376 4. TEH XIAO THONG – B032110141 Lab 6 – Project Cost Estimation 1. Identify one group project. 2. Prepare a sample cost estimation of the project. 3. Group manager has to submit the activity via Ulearn.
AUTOMOTIVE VEHICLES ENGINE HEALTH PREDICTION PROJECT COST ESTIMATE CREATED NOVEMBER 23, 2023
WBS ITEMS | #UNITS/HRS | COST/UNIT/HR (RM) | SUBTOTALS (RM) | WBS LEVEL 1 TOTALS (RM) | % OF TOTAL
1. Project Management |  |  |  | 214740 | 11.2162
Project Manager | 120 | 150 | 18000
Project Team Members | 1150 | 100 | 115000
Contractors (10% Of software development & testing) |  |  | 81740
2. Hardware |  |  |  | 274000 | 14.3115
Sensors and IoT Devices | 500 | 500 | 250000
Servers | 4 | 6000 | 24000
3. Software |  |  |  | 750000 | 39.1737
Licensed Software | 100 | 350 | 35000
Software Development* |  |  | 715000
4. Testing (10% of total hardware and softwarre cost) |  |  |  | 102400 | 5.3485
5. Training and Support |  |  |  | 190500 | 9.9501
Trainee cost | 100 | 650 | 65000
Travel cost | 10 | 1050 | 10500
Project team members | 1150 | 100 | 115000
6. Reserves (20% Of total estimate) |  |  |  | 382910 | 20
Total project cost estimate |  |  |  | 1914550 | 100
* See software development estimate
AUTOMOTIVE VEHICLES ENGINE HEALTH PREDICTION PROJECT DEVELOPMENT ESTIMATE CREATED NOVEMBER 23, 2023
1. Labor Estimate | #UNITS/HRS | COST/UNIT/HR (RM) | SUBTOTALS (RM) | CALCULATIONS
Contractor Labor Estimate | 3000 | 200 | 600000 | 3000*200
Project Team Member Estimate | 1150 | 100 | 115000 | 1150*100
Total labor estimate |  |  | 715000 | Sum above two values
2. Function Point Estimate** | QUANTITY | CONVERSION FACTOR | FUNCTION POINTS | CALCULATIONS
External Inputs | 10 | 4 | 40 | 10*4
External Interface Files | 3 | 7 | 21 | 3*7
External Outputs | 4 | 5 | 20 | 4*5
External Queries | 6 | 4 | 24 | 6*4
Logical Internal Tables | 7 | 10 | 70 | 7*10
Total function points |  |  | 175 | Sum above function point value
Java 2 Languange Equivalency Value |  |  | 46 | Assumed value from reference
Source Lines of Code (SLOC) Estimate |  |  | 8050 | 175*46
Productivity*KSLOC^Penalty (in months) |  |  | 29.28 | 3.13*8.05^1.072(see reference)
Total Labor Hours (200 hours/month) |  |  | 5856 | 29.28*200
Cost/labor hour (RM175/hour) |  |  | 175 | Assumed value from budget expert
Total Function Point Estimate |  |  | 1024800 | 5856*175
*Approach based on paper by William Roetzheim, "Estimating Software Costs," Cost Xpert Group, Inc. (2003) using the COCOMO II default linear productivity factor (3.13) and penalty factor (1.072).