## WBS with Gantt Chart
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE | [6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception & Initiation
1.1 | Project Charter | Leon W | 2022-03-12 | 2022-03-15 | 3 | 100%
1.1.1 | Project Charter Revisions | Kylie R | 2022-03-15 | 2022-03-16 | 1 | 100%
1.2 | Research | Pete S | 2022-03-15 | 2022-03-21 | 6 | 90%
1.3 | Projections | Steve L | 2022-03-16 | 2022-03-22 | 6 | 40%
1.4 | Stakeholders | Allen W | 2022-03-17 | 2022-03-22 | 5 | 70%
1.5 | Guidelines | Malik M | 2022-03-18 | 2022-03-22 | 4 | 60%
1.6 | Project Initiation | Malik M | 2022-03-23 | 2022-03-23 | 0 | 50%
2 | Project Definition & Planning
2.1 | Scope & Goal Setting | Steve L | 2022-03-24 | 2022-03-28 | 4 | 5%
2.2 | Budget | Allen W | 2022-03-29 | 2022-04-02 | 4 | 30%
2.3 | Communication Plan | Malik M |  |  | 0 | 0%
2.4 | Risk Management | Malik M |  |  | 0 | 0%
3 | Project Launch & Execution
3.1 | Status & Tracking | Pete S |  |  | 0 | 0%
3.2 | KPIs | Leon W |  |  | 0 | 0%
3.2.1 | Monitoring | Kylie R |  |  | 0 | 0%
3.2.2 | Forecasts | Kylie R |  |  | 0 | 0%
3.3 | Project Updates | Pete S |  |  | 0 | 0%
3.3.1 | Chart Updates | Malik M |  |  | 0 | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives | Steve L |  |  | 0 | 0%
4.2 | Quality Deliverables | Allen W |  |  | 0 | 0%
4.3 | Effort & Cost Tracking | Malik M |  |  | 0 | 0%
4.4 | Project Performance | Malik M |  |  | 0 | 0%
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
DURATION = DAYS([DUE DATE],[START DATE])

## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE | AUTOMOTIVE VEHICLES ENGINE HEALTH PREDICTION
PROJECT MANAGER | SIM WENG JIN
COMPANY NAME | TSLA SDN BHD
DATE | 15/10/2023 | [5 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[5 empty] | (days) | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Initiation Phase
1.1 | Project Goals & Objectives Definition | Sim | 31/5/2023 | 2023-07-06 | 7 | 88%
1.2 | Stakeholder Identification & Engagement | Thong | 31/5/2023 | 19/6/2023 | 19 | 70%
1.3 | Feasibility Assessment | Ang | 31/5/2023 | 15/6/2023 | 15 | 75%
2 | Planning Phase
2.1 | Data Strategy Development | Yuan | 2023-09-06 | 19/6/2023 | 10 | 50%
2.2 | Resource Allocation | Ang | 2023-09-06 | 21/6/2023 | 12 | 63%
2.3 | Risk Analysis & Mitigation | Ang | 19/6/2023 | 21/6/2023 | 6 | 77%
3 | Execution Phase
3.1 | Data Collection & Preparation | Thong | 2023-09-06 | 15/6/2023 | 5 | 90%
3.2 | Model Development | Sim | 15/6/2023 | 26/6/2023 | 11 | 100%
3.3 | Integration with Automotive Systems | Yuan | 20/6/2023 | 26/6/2023 | 6 | 82%
3.4 | Testing & Validation | Ang | 26/6/2023 | 30/6/2023 | 4 | 88%
4 | Controlling Phase
4.1 | Performance Monitoring | Sim | 28/6/2023 | 2023-03-07 | 5 | 40%
4.2 | Quality Control | Sim | 28/6/2023 | 2023-03-07 | 5 | 50%
4.3 | Feedback Integration | Yuan | 28/6/2023 | 2023-03-07 | 5 | 35%
5 | Closing Phase
5.1 | Documentation & Reporting | Thong | 28/6/2023 | 2023-04-07 | 6 | 64%
5.2 | Knowledge Transfer | Ang | 2023-03-07 | 2023-04-07 | 1 | 20%
5.3 | Lessons Learned & Project Review | Thong | 2023-03-07 | 2023-04-07 | 1 | 75%